## Proposal
[8 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11
[7 empty] | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F
TASK TITLE |  |  | START DATE | END DATE | TYPE | %COMPLETE | time axis 2023-11-03 to 2024-01-19
(other obligations)
|  | Course: EMOS & Stat consulting | 2023-09-01 | 2024-01-16
|  | TA: data vis | 2024-02-06 | 2024-06-10
|  | Course: Statistical computing | 2023-02-01 | 2024-05-28
CBS
|  | Onboarding | 2023-11-03 | 2023-11-03 |  | 100%
Superviour meetings
Thesis Proposal |  |  | 2023-11-06 | 2023-12-18
| Justification |  | 2023-11-06 | 2023-11-16
| Description |  | 2023-11-06 | 2023-11-16
Research Problem
Research aims
Research plan
Expected Results/end product
| Choose activities |  | 2023-11-21 | 2023-11-24
Problem specification |  |  | 2023-12-18 | 2024-01-20
Literature review
Defining the Research Question
Set Inclusion Criteria
Develop a Search Strategy
Preregistation: OSF |  |  | 2024-01-21 | 2024-01-23
*edited proposal + problem specification
| set up OSF page |  | 2024-01-21 | 2024-01-21
| write up |  | 2024-01-22 | 2024-01-23 | W

## Thesis
[5 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T
TASK TITLE | START | END | TYPE | DONE | time axis 2023-12-11 to 2024-08-27
Superviour meetings | 2023-04-11 | 2023-08-27 | @CBS | bar: 2024-04-18; 2024-04-23; 2024-04-30; 2024-05-14; 2024-05-21; 2024-06-04; 2024-06-11; 2024-06-25; 2024-07-02; 2024-07-09
Conduct initial searches to refine protocol | 2023-11-01 | 2023-12-15 | General | ✔
Define inclusion/exclusion criteria | 2023-11-01 | 2023-12-15 | General | ✔ | 2024-02-13: Wednesday mornings
proposal softdealine | 2023-12-18 | 2023-12-18 | "Deadlines" | ✔
Choose academic databases and search engine | 2023-12-20 | 2023-12-22 | General | ✔
Meta-gear testing | 2023-12-27 | 2023-12-27 | General | ✔
EMOS exam | 2024-01-09 | 2024-01-09 | (other obligations) | ✔
Search and export results into zotero | 2024-01-16 | 2024-01-16 | General | ✔
Complete searches and de-duplication | 2024-01-16 | 2024-01-16 | General | ✔ | bar: 2024-01-09
| 2024-01-21 | 2024-01-25 | Preregistation: OSF
Sample: Title and abstract screening | 2024-01-17 | 2024-01-27 | General | ✔
Data extraction: Sample set | 2024-02-12 | 2024-03-18 | Data extraction | ✔
draft: Intro + steps so far | 2024-03-18 | 2024-03-23 | Writing | ✔
Send jonas&joep intro + start of methods | 2024-03-25 | 2024-03-25 | "Deadlines" | ✔
Modeling: working out meta analysis methods | 2024-03-26 | 2024-03-29 | General | ✔
Send superviors preliminary analysis | 2024-04-02 | 2024-04-02 | "Deadlines" | ✔
Midway Meeting | 2024-04-03 | 2024-04-03 | "Deadlines" | ✔
Data extraction | 2024-04-01 | 2024-04-19 | Data extraction | ✔
Apply methods | 2024-04-20 | 2024-04-26 | General
Draft: results section | 2024-04-25 | 2024-05-02 | Writing |  | 2024-04-05: Friday morning-afternoon
Incorp. Feedback to intro and draft: methods + results | 2024-05-13 | 2024-05-17 | Writing
Send superviors: bullet points: methods, some preliminary analysis (meta analysis) | 2024-05-17 | 2024-05-17 | "Deadlines"
Feedback: sections so far | 2024-05-20 | 2024-05-28 | Feedback
Course: Statistical computing | 2024-04-01 | 2024-05-28 | (other obligations) |  | 2024-05-28: Exam
Analysis
Fix Papers
Meta- analysis
Meta-regression
incorparate feedback: Finalise intro and methods section | 2024-05-29 | 2024-05-29 | writing
analysis
finalise results | 2024-06-04 | 2024-06-09 | General
Make visulisation of results | 2024-06-10 | 2024-06-10 | General
finalise results | 2024-06-11 | 2024-06-13 | Writing
Submit: results draft | 2024-06-13 | 2024-06-13 | "Deadlines"
final feedback | 2024-06-25 | 2024-06-27 | Feedback
TA: data vis | 2024-02-06 | 2024-06-10 | (other obligations)
presenation prep | 2024-06-19 | 2024-06-21 | Writing
Presentation @ CBS | 2024-06-25 | 2024-06-25 | "Deadlines"
Final fixes | 2024-06-27 | 2024-07-01 | Writing
Hand in final manuscript to superviours | 2024-06-25 | 2024-06-25 | "Deadlines"
Reading group presenation | 2024-07-01 | 2024-07-01 | (other obligations)
Hand in reflections of activities | 2024-07-10 | 2024-07-10 | (other obligations)
local supervisor: provide a pass/fail grade | 2024-07-10 | 2024-08-09 | Feedback
Hand in final manuscript to internal reviewer | 2024-07-01 | 2024-07-01 | "Deadlines"
Offical deadline | 2024-08-13 | 2024-08-13 | "Deadlines" |  | 2024-08-13: X offical deadline
Thesis defience | 2024-08-27 | 2024-08-27 | "Deadlines"

## Thesis_old
[5 empty] | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M | T | W | T | F | M
TASK TITLE | START | END | TYPE | DONE | time axis 2023-12-11 to 2024-07-22
Superviour meetings | 2023-04-11 |  | @CBS | bar: 2023-12-26
TA: data vis | 2024-02-06 | 2024-06-10 | (other obligations) |  | 2024-02-13: Wednesday mornings
Conduct initial searches to refine protocol | 2023-11-01 | 2023-12-15 | General | ✔ | bar: 2023-12-26
Define inclusion/exclusion criteria | 2023-11-01 | 2023-12-15 | General | ✔ | bar: 2023-12-26
proposal softdealine | 2023-12-18 | 2023-12-18 | "Deadlines" | ✔ | bar: 2023-12-26
Choose academic databases and search engine | 2023-12-20 | 2023-12-22 | General | ✔ | bar: 2023-12-26
Meta-gear testing | 2023-12-27 | 2023-12-27 | General | ✔ | bar: 2023-12-26
EMOS exam | 2024-01-09 | 2024-01-09 | (other obligations) | ✔ | bar: 2023-12-26; 2024-01-09
Search and export results into zotero | 2024-01-16 | 2024-01-16 | General | ✔ | bar: 2023-12-26
Complete searches and de-duplication | 2024-01-16 | 2024-01-16 | General | ✔ | bar: 2023-12-26
Sample: Title and abstract screening | 2024-01-17 | 2024-01-27 | General | ✔ | bar: 2023-12-26
Data extraction: Sample set | 2024-02-12 | 2024-04-09 | General | bar: 2023-12-26
Intro + steps so far | 2024-03-18 | 2024-03-23 | Writing | bar: 2023-12-26
Send jonas&joep intro + start of methods | 2024-03-25 | 2024-03-25 | "Deadlines" | bar: 2023-12-26
Intro + steps so far | 2024-03-25 | 2024-03-30 | Feedback | bar: 2023-12-26
Modeling: working out meta analysis methods | 2024-03-25 | 2024-03-23 | General
Send superviors preliminary analysis | 2024-03-28 | 2024-03-28 | "Deadlines"
Course: Statistical computing | 2024-04-01 | 2024-05-28 | (other obligations) |  | 2024-04-05: Friday morning-afternoon; 2024-05-28: X
Midway Meeting | 2024-04-03 | 2024-04-03 | "Deadlines"
Draft: Method section | 2024-04-25 | 2024-05-02 | Writing | bar: 2023-12-26
Feedback? Method section | 2024-05-03 | 2024-05-09 | Feedback | bar: 2023-12-26
Analysis | 2024-05-10 | 2024-05-17 | General | bar: 2023-12-26
Outline results | 2024-05-18 | 2024-05-23 | Writing | bar: 2023-12-26
Send analysis/very drafty draft of results for feedback | 2024-05-24 | 2024-05-29 | Feedback | bar: 2023-12-26
Visulisation of results | 2024-05-30 | 2024-06-03 | General | bar: 2023-12-26
Draft: Results + Discussion | 2024-06-03 | 2024-06-13 | Writing | bar: 2023-12-26
Feedback? | 2024-06-14 | 2024-06-21 | Feedback | bar: 2023-12-26
Incorperate feedback Method, Results and Discussion | 2024-06-20 | 2024-06-25 | Writing
Final fixes | 2024-06-26 | 2024-06-28 | Writing
Hand in final manuscript | 2024-06-28 | 2024-06-28 | "Deadlines"
Thesis defience | 2024-07-01 | 2024-07-01 | "Deadlines"
Quality Assessment ?? | bar: 2023-12-26
Extras:
set up OSF page | 2024-01-21 | 2024-01-25 | Preregistation: OSF | bar: 2024-02-07 to 2024-02-13; 2024-02-28 to 2024-03-01
Formulas:
END = [START]+10
START = [END]-5